Valence HR Module

2-Week Sprint Plan

Scope: the 12 pending items from ERP_HR_updations.xlsx (Sheet1)

# Frappe / ERPNext Primer — Read This First, Both of You

Since you're both new to the framework, here are the five mechanisms you'll use over and over. Everything in this sprint is a combination of these.

| Concept | What it is | Where it lives |
| --- | --- | --- |
| DocType | A "table + form + logic" definition. Every entity (Leave Application, Employee, your custom Short Leave Ledger) is a DocType. Editing one via the UI generates JSON + Python files. | valence/doctype/<name>/ |
| Client Script (JS) | Runs in the browser on a form — controls what the user sees: hiding fields, showing alerts, auto-filling values, validating before submit. Doesn't touch the database directly. | public/js/*.js |
| Server-side hook (doc_events) | Python functions that run on the server when a document is saved/submitted/cancelled. This is where real rules are enforced — client scripts can be bypassed via API, server hooks can't. | doc_events/*.py, wired in hooks.py |
| Permission Query Conditions | A Python function that adds an extra SQL WHERE clause whenever a DocType's list is fetched — restricts which rows a user can see. | override/query.py |
| Workflow | ERPNext's built-in approval-chain feature (Draft → HOD Approved → Super HOD Approved → Approved). Usually configured through the UI. | Workflow record in UI |
| Whitelisted method | A Python function exposed as an API endpoint (@frappe.whitelist()), callable from JS or the mobile app. | override/whitelisted_method/ |
| Fixtures | Exported config (custom fields, property setters, workflows) so it's version-controlled and re-installable via bench migrate. | fixtures/*.json |

Note: Golden rule for this sprint: if a rule must always be true no matter how the data got there (e.g. "no more than 2 short leaves a month"), enforce it in a server-side doc_events hook, not just JS. JS is only for UX — it can be skipped via API/import; server hooks can't.

Also worth knowing: after adding a custom field or workflow via the UI, run bench export-fixtures (or use the manager's pre-set bench command) so it lands in fixtures/custom_field.json and your teammate gets it on bench migrate / git pull.

# Why Split This Way

The split is by file/module ownership, not just by item, so you're not both editing the same files. Two tracks:

- Track A — Attendance, Shift & Balance (Dev 1)

- Track B — Leave Application, Workflow & Access Control (Dev 2)

Note: Shared files — coordinate before editing: fixtures/custom_field.json, fixtures/property_setter.json, hooks.py. Rule: pull latest, add your entries at the end, commit + push immediately, ping the other person.

Git convention: one branch per item (feat/01-roster-weekly-off, feat/03-72hr-window, …), merge to dev as each item finishes — don't batch it all up for the end.

# Track A — Dev 1 (Attendance, Shift & Balance)

## #1  Shift Assign with Weekly Off through Roster

DAY 1–2

Goal: Let HR upload/define a roster in advance and have weekly-offs auto-assigned from it, instead of manually setting each employee's day off.

What to build:

- Check if a "Shift Assignment" or roster-style DocType already exists in standard ERPNext HR (Shift Assignment does — look at it in the UI first: /app/shift-assignment). You likely just need to extend it with a weekly-off field/pattern rather than build new.

- Add a custom field (e.g. weekly_off_day) to Shift Assignment via the UI → Customize Form → export to fixtures/custom_field.json.

- Edit shift_assignment_calendar.js so the calendar view reads/displays the assigned weekly-off day.

- If "assign via roster in bulk" doesn't exist, you may need a small new DocType (e.g. Roster Plan) with a server method that bulk-creates Shift Assignment records — this is the heavier part.

Files: shift_assignment_calendar.js, fixtures/custom_field.json, possibly new doctype/roster_plan/

## #2  Shift Assign in Employee Checkin

DAY 3–4

Goal: When an employee punches in/out (Employee Checkin), auto-detect and assign the correct shift based on their punch time pattern.

What to build:

- Server hook in doc_events/attendance.py (or a new employee_checkin.py if it doesn't exist) on the before_insert/validate event of Employee Checkin — compare punch time against defined shift start times and set the shift field automatically.

- If "pattern-based" means matching against multiple shift types (General/Rotational), you'll need a small lookup: find the shift type whose start-time window contains the punch time.

- Client-side (attendance.js) only needed if you want to show the detected shift live on the form before save — optional, nice-to-have.

Files: doc_events/attendance.py (or new doc_events/employee_checkin.py, registered in hooks.py's doc_events)

## #6  Short Leave Management

DAY 5–6 (HALF)

Goal: Employees apply for short leave (max 2 hrs) through the portal; system blocks more than 2 per month.

What to build:

- short_leave_ledger doctype already exists — check its current fields/purpose first (view the folder).

- Server hook: validate on Short Leave Ledger (or on submit) → count existing entries for that employee in the current month; if count ≥ 2, frappe.throw() a clear error.

- Make sure the 2-hour cap is validated too (duration field check).

Files: doctype/short_leave_ledger/short_leave_ledger.py

## #8  Backdated Leave Control

DAY 6 (HALF)–7

Goal: Employees can't cancel/modify a leave for a past date; only HR can, after checking attendance.

What to build:

- Server hook (on_update/before_cancel) on Leave Application: if from_date is in the past AND the logged-in user's role isn't "HR Manager"/"HR User", block the cancel/amend with frappe.throw().

- Since Leave Application is a standard doctype, put this in a new doc_events/leave_application.py file (register in hooks.py) rather than editing core ERPNext code.

Files: new doc_events/leave_application.py, hooks.py

## #9  Automatic Leave Balance Update

DAY 8–10 — HEAVIEST ITEM, BUDGET THE EXTRA DAY

Goal: Leave balances auto-update quarterly from actual working days; HR can manually enter working-days data if auto-calc isn't possible; balances credited automatically off that.

What to build:

- This is a scheduled job, not a doc-event. In hooks.py, add a scheduler_events entry (e.g. "cron": {"0 0 1 */3 *": [...]} — quarterly) pointing to a Python function.

- That function: pull each employee's working-days count (from Attendance records) for the quarter, apply the leave policy's accrual rule, and create/update Leave Ledger Entries (ERPNext has a built-in Leave Ledger Entry doctype — use it rather than reinventing).

- For the manual-fallback path: add a small DocType or a simple field where HR keys in working days per employee/quarter when auto-calc fails; your scheduled function should check for this override first.

Files: new function, likely in override/whitelisted_method/ or a new valence/tasks.py, wired via hooks.py's scheduler_events

# Track B — Dev 2 (Leave Application, Workflow & Access Control)

## #3  72-Hour Leave Application Window

DAY 1

Goal: Block leave applications submitted less than 72 hours before the leave start date (confirm with manager: is it 72 hrs before start date, or within 72 hrs of an event — clarify before coding).

What to build:

- Simple server hook: validate on Leave Application → compare frappe.utils.now_datetime() against from_date; if the gap is under 72 hours, frappe.throw().

- Quick win — good first task to get comfortable with doc_events.

Files: new doc_events/leave_application.py — same file Dev 1 touches for #8: talk to each other before both editing this, or split into two clearly-commented functions, or message in chat who edits first each day.

## #4  Extended Leave Approval Workflow

DAY 2–3

Goal: Leave of 3+ days needs an additional Super HOD approval step on top of the normal approval.

What to build:

- Look at the existing Workflow record for Leave Application in the UI (/app/workflow). Add a new state ("Pending Super HOD Approval") and transition rule, condition: doc.total_leave_days >= 3.

- Workflow conditions are usually just a Python expression typed into the workflow transition's "Condition" field in the UI — no code needed for the branching itself.

- Only write Python in doc_events/workflow_state_change.py if you need extra logic when the state changes (e.g. notify the Super HOD).

- Export the workflow config to fixtures (workflow.json / fixtures) so your teammate gets it.

Files: Workflow record (UI, export to fixtures), doc_events/workflow_state_change.py

## #5  Department-wise Leave Access Control

DAY 4–5

Goal: Employees/HODs see only their department's leave data; HR sees everything.

What to build:

- This is a textbook Permission Query Condition. In override/query.py, write a function that returns a SQL WHERE clause like "department = '{}'".format(user_department), and return an empty condition (full access) if the user has the HR role.

- Register it in hooks.py under permission_query_conditions = {"Leave Application": "valence.override.query.leave_application_query"}.

- Also double check standard Role Permission Manager settings (UI) — sometimes you need both the query condition AND a "User Permission" or role-level restriction for it to fully lock down.

Files: override/query.py, hooks.py, possibly Role Permission settings (UI/fixtures)

## #7  OD/WFH Workflow

DAY 6–7

Goal: OD and WFH requests follow the same approval chain as leave (no self-approval, HOD + Super HOD mandatory, reason required).

What to build:

- Check first: does ERPNext already have an "OD/WFH" doctype, or is Attendance Request the closest standard doctype? Look before building new — reusing a standard doctype and adding a workflow is much less work than a new DocType.

- If nothing fits, create a new DocType (OD WFH Request) with fields: employee, type (OD/WFH), date(s), reason (mandatory field — set reqd: 1), and attach the same Workflow pattern you built for #4.

- Add a validate hook to block a user approving their own request (compare frappe.session.user against the requester).

Files: new doctype/od_wfh_request/ (if needed), Workflow record, doc_events/workflow_state_change.py

## #10  Leave on Present Day Restriction

DAY 8

Goal: Can't apply leave for a day already marked Present in Attendance; HR can override.

What to build:

- validate hook on Leave Application: query the Attendance doctype for that employee+date; if status is "Present" and the logged-in user isn't HR, frappe.throw().

Files: same doc_events/leave_application.py as #3/#8 — again, coordinate with Dev 1.

## #11  Resignation Option

DAY 9

Goal: Resigned employees can only apply LWP/Sick Leave — not CL/EL.

What to build:

- validate hook on Leave Application: check frappe.db.get_value("Employee", employee, "status") (or "relieving_date" is set) → if resigned, only allow leave_type in ["Leave Without Pay", "Sick Leave"], else throw.

Files: same shared doc_events/leave_application.py

## #12  Mobile App Approval

DAY 9 (HALF)–10

Goal: HODs approve/reject leave from the mobile app.

What to build:

- Frappe's mobile app generally reuses whitelisted server methods. Check first if the standard Leave Application approve/reject action already works on mobile out of the box (it often does, since it's just a doc update_status call) — this may need zero new code, just verification.

- If a custom approval action was added for #4's extra Super HOD step, make sure that action is also exposed as a @frappe.whitelist() method (not just a UI button) so the mobile app can call it.

Files: override/whitelisted_method/

# Shared Checkpoints

- End of Day 5 (Fri, Week 1): merge everything to dev, integration-test together, resolve any conflicts in doc_events/leave_application.py (both of you touch this file — see notes above).

- Day 10: cross-test Track A's balance/attendance logic against Track B's leave rules (e.g. does #10's "Present day" check correctly read Track A's attendance data? does #9's balance credit interact correctly with #4's approval workflow?).

# Practical Tips Since You're Both New to Frappe

- Use bench console to poke at data and test small snippets (frappe.get_doc(...), frappe.db.get_value(...)) before writing them into files — much faster feedback loop than save-and-reload.

- frappe.throw("message") is how you block a save with an error the user sees — you'll use it constantly.

- After any DocType/Workflow/Custom Field change in the UI, remember to export to fixtures, or it only exists on your machine.

- bench migrate after pulling your teammate's changes to apply their new custom fields/doctypes locally.

- When stuck, check if standard ERPNext HR already does 80% of what you need (Shift Assignment, Attendance Request, Leave Ledger Entry) — extending is much faster than building fresh.